## ProjectTeam
Name | GitHub Alias

## Product Backlog
ID | Story Name | Description | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1 | Admit new patient | a new patient makes contact on reference from Dr. Boehm. After creating a new patient record, the medical history... | high | 100h | 100h | 0h | waiting
2 |  |  | medium | 200h | 180h | 50h | work in progress
3 |  |  | low | 400h | 450h | 350h | done
4 |  |  | high | 16h | 40h | 12h | cancelled

## Sprint Backlog
ID | Sprint | Name | Description | Components | Owner | Reviewer | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1.1 | 2 | Patient Model | Data model for patient record needs to be created based on standard.... | Database | Martin | Hans | medium | 2 | 2 | 0 | waiting
1.2 | 2 |  |  | UI, Controller | Hans | Jennifer | high | 8 | 6 | 4 | work in progress
1.3 | 1 |  |  | All | Martin | Tom | high | 16 | 20 | 20 | done
2.1 | 1 |  |  | Database | Tom | Martin | low | 4 | 10 | 4 | cancelled
2.2 | 2 |  |  | Main Window | Jennifer | Martin | high | 8 | 6 | 5 | work in progress

## BurndownChart
Sprint | Time of Record | Remaining Effort | Remaining Ressources
1 | 2015-09-15 | 200 | 200
1 | 2015-09-16 | 190 | 180