## ProjectTeam
Name | GitHub Alias
Sinthujah Kaneshan Balasubramaniam | Skaneshan
Simon Herrmann | herrs2
Lars Gertsch | gertl1
Silas Stulz | Hyferion
Steve Blaser | bluedemise
Fabio Caggiano | jmpout

## Product Backlog
ID | Story Name | Description | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1 | Recipe Order | User can order a prescription for a medicament. If approved the user can dowload the prescription and print it @ home |  | 40 |  |  | waiting
2 | Information | User can inform himself about his relatives desease and has helpful links provided |  | 10 |  |  | waiting
3 | Mainview | User can view the MainView and further navigate to other MenuPoints |  | 15 |  |  | waiting
4 | Chatroom | User can enter a Chatroom where he can chat with other Users about his situation |  | 35 |  |  | waiting
5 | Calendar | User can view a weekly activity calendar of his relatives and edit/add tasks |  | 25 |  |  | waiting
6 | File | User can dowload stored files from the patient or the doctor (e.g. Recipes, Drawings) |  | 20 |  |  | waiting
7 | Userlogin | User can login with a registered account of himself |  | 35 |  |  | waiting
180

## Sprint Backlog
ID | Sprint | Name | Description | Components | Owner | Reviewer | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1.1 | 2 | Patient Model | Data model for patient record needs to be created based on standard.... | Database | Martin | Hans | medium | 2 | 2 | 0 | waiting
1.2 | 2 |  |  | UI, Controller | Hans | Jennifer | high | 8 | 6 | 4 | work in progress
1.3 | 1 |  |  | All | Martin | Tom | high | 16 | 20 | 20 | done
2.1 | 1 |  |  | Database | Tom | Martin | low | 4 | 10 | 4 | cancelled
2.2 | 2 |  |  | Main Window | Jennifer | Martin | high | 8 | 6 | 5 | work in progress

## BurndownChart
Sprint | Time of Record | Remaining Effort | Remaining Ressources
1 | 2015-09-15 | 200 | 200
1 | 2015-09-16 | 190 | 180