## ProjectTeam
Name | GitHub Alias
Sinthujah Kaneshan Balasubramaniam | Skaneshan
Simon Herrmann | herrs2
Lars Gertsch | gertl1
Silas Stulz | Hyferion
Steve Blaser | bluedemise
Fabio Caggiano | jmpout

## Product Backlog
ID | Story Name | Description | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1 | Recipe Order | User can order a prescription for a medicament. If approved the user can dowload the prescription and print it @ home | medium | 40 |  |  | waiting
2 | Information | User can inform himself about his relatives desease and has helpful links provided | medium | 10 |  |  | waiting
3 | Mainview | User can view the MainView and further navigate to other MenuPoints | high | 15 |  |  | waiting
4 | Chatroom | User can enter a Chatroom where he can chat with other Users about his situation | medium | 35 |  |  | waiting
5 | Calendar | User can view a weekly activity calendar of his relatives and edit/add tasks | high | 25 |  |  | waiting
6 | File | User can dowload stored files from the patient or the doctor (e.g. Recipes, Drawings) | high | 20 |  |  | waiting
7 | Userlogin | User can login with a registered account of himself | low | 35 |  |  | waiting
180

## Sprint Backlog
ID | Sprint | Name | Description | Components | Owner | Reviewer | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1.1 | 1 | MainView | Create MainView with Buttons and Links to other Views | MainView | Sinthya | Silas | high | 9 |  |  | waiting
1.2 | 1 | ChatView | Create the Barebone of ChatBox | ChatRoom | Silas | Synthia | high | 9 |  |  | waiting
1.4 | 1 | CalendarView | A List of all Days with Tasks and a add Task Button | Calendar | Fabio | Steve | high | 9 |  |  | waiting
1.5 | 1 | TaskView | A View of Task with related Files added and Edit Button | Calendar | Steve | Fabio | medium | 9 |  |  | waiting
1.6 | 1 | OrderView | A View for the Order of Recipes | Order | Simon | Lars | medium | 9 |  |  | waiting
1.7 | 1 | View of Recipes | A View of owned Recipes | Order | Lars | Simon | medium | 9 |  |  | waiting

## BurndownChart
Sprint | Time of Record | Remaining Effort | Remaining Ressources
1 | 2015-09-15 | 200 | 200
1 | 2015-09-16 | 190 | 180